## Sheet1
ID | Risk | Probability | Impact | Priority | Mitigation | Contingency | Owner | Status
R-01 | Loss or corruption of CivicConnect data may affect data integrity and service continuity. | Medium | High | High | Define backup, recovery and transactional integrity requirements before database technology is finalised. | Restore data from a verified backup and investigate the cause of corruption before normal operation resumes. | Megan Wathen | Open
R-02 | Failure or unavailability of external or internal service interfaces may prevent residents or administrators from completing system functions. | Medium | High | High | Identify service dependencies and define availability, error-handling and recovery requirements. | Provide controlled failure handling and restore/reconnect affected services when available. | Megan Wathen | Open
R-03 | Weak authentication, token or session management could allow unauthorised access to CivicConnect functions or information. | Medium | Very High | High | Define secure authentication, authorisation and session-management requirements before implementation decisions are made. | Revoke compromised credentials/sessions, investigate the incident and apply corrective access controls. | Megan Wathen | Open
R-04 | Failures or abnormal system behaviour may not be detected quickly enough if monitoring and logging requirements are inadequate. | Medium | Medium/High | Medium/High | Define logging, monitoring and alerting requirements before deployment decisions are made. | Investigate logs and system evidence, isolate the affected component and perform recovery procedures. | Megan Wathen | Open